Project Management-Xemba Translations

Student’s Name:

Professors Name:

Course:

Date:

Project Management-Xemba Translations

An analysis of the current risks that the project is likely to encounter will enhance the successful completion of the project as the assessment will include mitigation measures. The mitigation strategies are necessary as the risks slow down and jeopardize the entire project. The potential risks in the project are described in the table below.

| Risk | Impact | Likelihood of Occurrence | Degree of impact | Initial Action | Team Member Responsible | Strategies for prevention and mitigation |
| --- | --- | --- | --- | --- | --- | --- |
| Lack of backup systems | Loss of data that is crucial for the company. | H | H | Backup all the information in the organization in storage devices and install backup software in the company’s computers. | Elizabeth | Installing a backup software that will be used to back up all the company’s data. |
| Poor Internet connectivity | Sending and receiving emails will be delayed and conducting video conferences will also be a challenge for the team members involved in the project. | M | H | Having an alternative internet provider in the organization or making use of mobile internet device. | Phoebe | Hotspots can be provided to employees experiencing poor internet connectivity |
| Hackers could access confidential information | This could cause the loss of important company data | L | H | The IT department ensures that the log confidential information is password protected and have software that eliminates any intrusion by hackers | Malinda | Conduct regular network scans and ensure that the anti-virus and anti-malware software are up to date |
| Unauthorized access of company information by outsiders by using the telecommuters computer | Competitors may access important company information. | H | H | Have strict security policies in place for the telecommuters. | Jackson | Introduce authentication processes and strict passwords to reduce access of the company computers by strangers |
| Reduced productivity because of lack of supervision | Work overload since work is not completed on time | H | M | Introduce regular performance evaluations and take action on underperforming employees | Elizabeth | Introduce a software that monitor when employees log on to their computers |

Metrics of Measurement

Scheduled Variance percentage is one of the methods that will be used to track the status of the project by measuring how far behind or ahead the scheduled project is (Pritchard, 2014). A positive SV percentage indicates that the project is ahead of the schedule while a negative number indicates that the project is behind the schedule.

Cost variance percentage is the second metric that can be used to measure the performance of a project (Pritchard, 2014). The metric determines whether the project is over or under the budget at any point. Just like the scheduled variance method, the positive and negative results indicate the good and bad conditions of the project where the positive results suggest that the project is within the stipulated budget while the negative results show that the project is over the budget.

The other two methods used to measure the project's performance are cost performance index and schedule performance index. Where the cost performance index helps a project manager identify the efficiency of the project’s expenses and the project’s earnings compared to the expenses. An answer that is less than one indicates that the project is over the budget while an answer greater than one indicates that the project is performing lower than the budget. The scheduled performance index, on the other hand, determines the progress of the project in comparison to the planned progress (Cuyler, & Holland, 2012). An answer greater than one after calculating the scheduled performance index indicates that the project is ahead of schedule while a number less than one shows that the project is behind schedule.

The metrics are appropriate for the project because the cost and time of the project have already been estimated making it easy to calculate the cost and schedule variance as well as the cost and schedule performance index. Thus, this makes it easy to determine the current performance of the project and its completed percentage.

Calculations

| Task | Total cost | Baseline | Variance | Actual | Remaining | Completed Percentage | Cost Variance | CPI |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Computer inventory and requirements | $ 27,715.16 | $25,021.43 | ($2,693.73) | $ 27,715.16 | $0.00 | 100% | (9.72%) | 0.90 |
| Computer support | $ 13,500 | $11,310 | ($2,190) | $ 10,365 | $3,135 | 81% | (16.22%) | 1.01 |
| Technical support | $11,380 | $11,500 | $ 120 | $9,313.33 | $2,066.67 | 74% | 1.05% | 0.84 |
| Document Servers | $20,148 | $18,964 | ($1,184) | $13,658 | $ 6,490 | 68% | (5.88%) | 0.94 |
| Shared Drives | $ 20,224.80 | $17,844 | ($2,380.80) | $12,733 | $7,491 | 65% | (11.77%) | 0.88 |
| Firewalls | $31,320 | $ 31,800 | $480 | $7,320 | $ 24,000 | 37% | 1.53% | 0.98 |
| FTP sites | $43,133.34 | $ $42,310 | ($ 823.34) | $16,181.33 | $26,952 | 23% | (1.91%) | 1.02 |
| Web-based Meeting | $ 24,480 | $ 14,580 | ($9,900) | $15,300 | $9,180 | 60% | (40.44%) | 0.60 |
| Totals | $ 191,901.30 | $ 173,329.43 | ($18,571.87) | $112,586.02 | $ 79,315.27 | 64% | (9.68%) | 0.90 |

| Task | Work | Baseline | Variance | Actual | Remaining | Completed Percentage | Schedule Variance | SPI |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Computer inventory and requirements | 375.95 | 340 | (35.95) | 375.95 | 0 | 100% | (9.56%) | 0.90 |
| Computer support | 258 | 210 | (48.00) | 192 | 66 | 74% | (18.60 %) | 0.81 |
| Technical support | 197.33 | 200 | 2.67 | 160.67 | 36.67 | 81% | 1.35% | 1.01 |
| Document Servers | 356 | 330 | (26.00) | 242 | 114 | 68% | (7.30%) | 0.93 |
| Shared Drives | 351.2 | 310 | (41.20) | 228.8 | 122.4 | 65% | (11.73%) | 0.88 |
| Firewalls | 417.6 | 424 | (12.67) | 97.6 | 320 | 23% | 1.53% | 1.02 |
| FTP sites | 621.67 | 609 | 6.40 | 230.87 | 390.8 | 37% | (2.04%) | 0.98 |
| Web-based Meeting | 430 | 270 | (160.00) | 260 | 170 | 60% | (37.21%) | 0.63 |
| Totals | 3007.75 | 2693 | (314.75) | 1787.89 | 1219.87 | 64% | (10.46%) | 0.90 |

From the calculations, it is evident that the project is behind schedule and over the budget. The over budget is caused by tasks such as computer inventory and requirements. Furthermore, the calculations indicate that the project’s expenditure is more hence some of the tasks may first require approval by the management. Thus, necessary actions have to be taken by the project committee to ensure that the expenditures are reduced and the project is within the stipulated budget and schedule.

Problems that Exist and Possible Solutions

The calculations indicate that the project is already over the estimated budget which means that the project will be completed with more funds than estimated. Thus, it is necessary for the project manager to make significant adjustments to the existing budget to ensure that the project is completed within the set targets. For instance, the computer inventory and requirements cause an over-budget hence Xemba Translations could consider purchasing desktops because they are less costly than the portable computers. This will save the organization some money as well as reduce the hardware expenses enabling the company to save some money to purchase more equipment.

Another significant problem identified is the share drives which exhibit an over budget after the calculation of cost variance percentage. The installation of the share drives is attributed to be the leading cause a lot of expenses to the organization. Currently, Xemba Translations has 173 employees who might be telecommuting. However, with time the company is anticipated to grow and the number of telecommuters is also likely to increase. Consequently, the demand for more shared and storage devices will increase making the budgets to also increase. To solve this problem, the company should consider a cloud-based solution that will save costs and prevent budget overruns even in future as well as outsource the share drives from another company.

The third problem involves the scheduling delays which may affect the implementation process of the project. If the project manager does not come up with solutions for this problem, then the project will end after the target date since the project is only 64% complete as per the calculations. Several factors such as the process of identifying the staff and the resources required took a considerable amount of time and the bad weather conditions also caused some delays in completing the web-based meeting pilot tests. Even though bad weather conditions are inevitable, the project manager should have strategies in place that counter such problems by having back up plans. Furthermore, a more effective method should be developed to use it in the selection process of the project team members.

Executive Summary

Xemba Translations is currently working on a project that aims to expand telecommuters. The project has taken place for 123 days and is only 64% based on the calculations made in B2. However, the project has a budget overrun of 9. 68 % and is also behind schedule by forty working days. The cause of the budget overrun is caused by factors such as computer inventory and requirements where additional computers were purchased and this had not been included in the original project forecast. Moreover, the team involved in the project had to take time and identify the software upgrades for the additional computers which used up time that could have been used to do other activities in the project. The increased cost in share drive because of the increased number of telecommuters was also to blame for the budgets overrun in the project. The costs were anticipated to increase with time as the number of telecommuters in the company increased. However, outsourcing the share drives and a cloud-based solution was suggested to be strategies that could best solve this issue.

In the process of evaluating the performance of the project, several risks were identified. A risk matrix was developed to better understand the risks, their impact, and strategies that an organization could adopt to mitigate them. Among the risks identified included the lack of backup systems, poor internet connectivity, hackers who could access confidential information, reduced productivity and unauthorized access to company information by outsiders. The lack of backup systems was identified to be a risk that could have a great impact to the organization hence installing backup software was identified to be the best strategy to mitigate such a risk in the organization. Poor internet connectivity would affect the flow of work and employees would be behind schedule which would have a great impact on the organization. As a result, hotspots using mobile phones was determined to be the best strategy to prevent the occurrence of this risk.

Telecommuting also increased the risk of hacking since employees may occasionally use public networks. As a result, the IT department must make sure that all the confidential information in the company is password protected and that all the antivirus and antimalware software is up to date to prevent the intrusion by the hackers. As for reduced productivity associated with minimal supervision, a software that monitors the employees log in was proposed to be the best mitigating strategy for such a risk. Lastly, introducing authentication process and strict passwords was suggested to be the best strategy to prevent unauthorized access to company information by outsiders.

From the in-depth analysis of the project’s current performance and the underlying risks, it is evident that action must be taken to mitigate the overruns in costs and to ensure that the project is within the schedule (Stile, 2009). The team members involved in the project should take the time to come up with ways to reduce the costs and time taken to complete the projects. One of the recommendations for this will include purchasing desktops which are cheaper, rewarding the employees who complete their work within the scheduled time to enhance productivity, having strong internet connectivity and having regular performance evaluations to assess the employees outcome to ensure that the company’s quality standards are met as well as the project expectations are met. Therefore, this will facilitate the successful completion of the company’s project within the scheduled time.

References

Cuyler, R., & Holland, W. E. (2012). Implementing telemedicine: Completing projects on target on time on budget. Bloomington, IN: Xlibris Corp.

Pritchard. C. (2014). The Project Management Communications Toolkit, Second Edition.  Boston: Artech House

Stile, A. (2009). Practice standard for project risk management (1st Ed.). Newtown Square, Pa.: Project Management Institute.