## Sheet1
Project Completion Plan
Student Name: Bruce Nsubuga
|  |  | SP124 |  |  |  | SU124 |  |  |  | FA124 |  |  |  | SP125 |  |  |  | SU125
|  |  | NU740 |  |  |  | NU726 |  |  |  | NU727 |  |  |  | NU741 |  |  |  | NU742
DNP Activity/Task | Start | End | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Choose practice prolem for EBP project | SP124 - Jan | SP124-Jan
SPP PowerPoint | SP124-Mar | SU125-Aug
SPP Paper | SP124-Mar | SU125-Aug
SPP Poster | SP124-Mar | SU125 - Aug
Chapter I | SP124-Mar | SU125 - Aug
Chapter II | SU124 - Jun | SU125 - Aug
Chapter III | FA124 - Sep | SU125 - Aug
Chapter IV | SP125-Jan | SU125 - Aug
Chapter V | SU125- May | SU125 - Aug
Proposal Defense | SP124-Mar | SU125 - Aug
IRB/SitePermission | FA124 - Sep | SP125 - Jan
IRB Regis | FA124-Sep | SP125-Jan
SPP Conduct the Study | SU125-May | SU125 - Aug
Portfolio | SP124-Mar | SU125 - Aug