Implementation plan

Pre-intervention period

(AHRQ)obtain leadership buy-in and identify champion

- Recruitment of Participants:

The practicum site has approved the introduction of the teach-back method as a quality improvement on the standard of practice for interacting with bipolar disorder patients. As such, no informed consent is required (WE MAY NOT NEED IRB APPROVAL BUT LACK OF CONSENT IN USA IS NEW TO ME). The announcement about the project will be done on all routine staff meetings held over a period of two weeks prior to the commencement of the intervention. The notice will outline the purpose of the intervention, the intervention period, the schedules for individualized-training sessions, and dates for the weekly huddles. Consequently, the notice will emphasize on the voluntary participation and exit at any period of the intervention without retribution. Printed and digital copies of the notice will be available for pick up during the staff meeting announcement.

- Pre-intervention data collection

Eligible Staff members who voluntarily agree to participate will complete the Confidence and Conviction Scale (CSS) and book an appointment for their training session. To protect confidentiality and easy data handling the enrolled participants will be asked to create and label their CSS form with a four figure identifier that they can remember over a period of 10 weeks. Consequently, a sealed box labeled ‘Pre-intervention’ with an opening to ballot the filled CCS forms will be provided. Hourly appointments to teach-back training sessions will be given to enrolled participants in line with the practicum site authorisation of a maximum of four training sessions per day for one week.

Week 1: KTA model phase 4. Select, tailor, implement intervention

- The teach-back training

Each enrolled participant will receive an Individualized 60 minute teach-back training session consisting of:

- A short review of why teach-back use is recommended for bipolar patients

(readmission rates, medication non-adherence, etc) and instances when required (medication education, follow-up information etc).

-approximately 10 minutes

- “Always teach back Toolkit”

- Interactive module- The participant will be introduced to the online interactive training -approximately 30 minutes per session

- Teach back resources- Interactive module and handouts- teach-back guide (1page) and teach back aid (1 page)

-approximately 10 minutes

- Role Play: 5 minutes

I will assume the roles of clients with bipolar disorder reporting to the clinic for readmission, first visit, refills, follow-up etc and ask the participants to attend to my needs using the teach-back method. Alternatively, the participants will be free to play the role of the patient and I assume the role of the care provider.

-approximately 5 minutes

- Intervention guidelines

I will request the participants to adhere to the teach-back toolkit when attending to patients with Bipolar Disorder. To offer a real time support system to the participants, I will also provide my contact and the project heroes' contact.

Week 2-9

KTA Model  phase 5. Monitor knowledge use

Week 2-9:  Implementation phase

- Staff will be required to use teach-back when caring (discharging) patients with bipolar

- Weekly morning huddles- Note challenges,Offer tips

- Project hero

- (saw them in DNP manuscript)

Week 10 -11

KTA Model Phase 6: Evaluate Outcomes

- Post-intervention data collection

During the 10th week, the participants will be asked to complete the post intervention CCS form and drop it in a sealed box labeled ‘post-intervention’. Emphasis will be made to label it with the unique number they created when filling pre-intervention CCS form.

- Data cleaning and entry

I will retrieve the pre-intervention CCS forms from the sealed labelled ‘pre-intervention’, check them for completeness and use them to create a data set in the SPSS application. I will retrieve the post-intervention CCS forms from the sealed box labelled ‘post-intervention’, check them for completeness and update the data set.

The CCS is composed of four questions (ref).

Question 1 requires the participant to rate their conviction on the importance of the teach-back method on a 1-10 point likert scale (1- not at all important to 10-very important).

Question 2 utilizes a similar Likert scale (1-not confident at all to 10-very confident) to rate participants' ability to use the teach-back method.

Question 3 requires the participants to select how often they use the teach-back method from the five choices provided.

Question 4 asks the participants to select the elements of effective teach-back they have been using for more than half the time in the past work week.

- Data analysis

Each Question will be analyzed separately. In question 1 and 2 the pre-intervention mean score of the participants will be compared with the post-intervention mean score of the participants. A paired t-test will be used to determine the statistical significance with a score of 0.05 (awaits expert input) In question 3 (5 choices) and 4 (10 elements) frequencies, percentages and descriptive statistics will be used to analyze the data of each response made by the participants. A paired t-test will be used to compare the pre-intervention and post-intervention average scores of each question to determine the statistical significance of observed changes in teach-back consistency and teach-back behaviors respectively. (awaits expert input)

- completion of the manuscript, preparation of dissemination material (poster

Week 12 KTA model 7:  Sustain knowledge

Immediate: Dissemination of results- posters, seminars, conferences, publication

Short-term: Hand-over the initiative

Long-term:  Replication in other conditions and settings.