Project Manager Roles and Responsibilities

- Detail your implementation plan for your DNP project. Include milestones for a timeframe of 8-12 weeks.

The project is set to take 12 weeks where activities or tasks will be assigned in sections to cover the entire period. For this reason, week 1 will be meant for project preparations where the major activities will include securing leadership buy-in and approvals, identification of participants and assessing staff confidence before the teach-back method is employed. Securing of leadership buy-in will be the first step so that other activities may take place as the buy-in will ensure that the project is fully supported by the leaders (Dunlap & Waldrop, 2024). On the other hand, identifying participants such as nurses and other staff members will help in planning for the next phase which involves applying the intervention to the participants.

Week 2 and 3 will be allocated for conducting the teach-back method by providing case-study discussion and role-playing exercises. The activity will ensure that nurses understand and utilize the method. Week 4 and 5 will cover the first implementation phase where the staff members will apply the teach-back method during patient interactions. Another important activity for week 4 and 5 will be to monitor staff engagement while providing real-time feedback. According to McCormack (2021), engaged employees are crucial to an organization’s success due to improved quality of care. The second implementation phase will be done in from week 6 to 7 by continuing the teach-back method and conducting one-on-one coaching where necessary. Collecting qualitative feedback will also be done during week 6 to 7 to ascertain understanding of the teach-back method.

Data collection and evaluation will be conducted from week 8 to 9 through a survey to assess staff confidence. A comparison of the pre and post-intervention data will also be done to determine the rate of confidence and conviction among nurses. It is crucial to identify areas of challenge by assessing the process and its outcomes to acknowledge the effectiveness of a project (Bradshaw & Vitale, 2024). Additional qualitative feedback will be conducted from week 10 to 11 to identify trends or challenges and refinement areas. Finally, week 12 will be set aside for reporting and project conclusion. The findings will be presented to stakeholders while providing recommendations for sustaining the use of teach-back method.

- Explicate how you will gauge the success of your project.

The project’s success will be gauged through pre and post-intervention surveys to help measure conviction levels and staff confidence before and after implementing the teach-back method. Additionally, staff members will be assessed regarding their proficiency in utilizing the teach-back method through observation and feedback from self-reported experiences. Patient outcomes will also be used to evaluate whether patients have reported improved understanding of their treatment and condition, a crucial component in measuring the success of a project (Turkson‐Ocran et al., 2020). Ultimately, the adoption and sustainability of the teach-back method will help to determine whether staff members are continuing to use the teach-back method independently past the study period.

- What is your role in managing your project budget and resources in the planning and implementation phases?

My role in managing the project budget and resources in the planning and implementation phase includes identifying expenses for staff time and training materials for participation (Fauer & Wilson, 2024). Securing funding and resource allocation will also be done in the planning phase by seeking external grants where necessary and organizational support while planning for space, personnel and technology required. Further, the implementation phase will involve monitoring resource use to ensure efficient use of materials and time while minimizing disruptions to workflow (Fauer & Wilson, 2024). Adjustments will also be made where necessary through reallocation of resources based on emerging needs. Consequently, expenditures should be tracked and justifications made to stakeholders regarding resource allocation.

References

Bradshaw, M. J., & Vitale, T. R. (2024). The DNP project workbook: A step-by-step process for

success. Springer publishing company.

Dunlap, J. J., & Waldrop, J. B. (2024). Encouraging Evidence-Based Practice Quality

Improvement Enterprise Engagement. The Journal for Nurse Practitioners, 20(5). https://www.npjournal.org/article/S1555-4155(24)00102-8/pdf

Fauer, A. J., & Wilson, R. (2024). Hit the ground running: Starting to manage personnel and

budgets as a new nurse scholar. Asia-Pacific Journal of Oncology Nursing, 100533. https://doi.org/10.1016/j.apjon.2024.100533

McCormack, H. (2021). Improving employee engagement on an inpatient unit: a quality

improvement project. https://scholars.unh.edu/scholarly_projects/56?utm_source=scholars.unh.edu%2Fscholarly_projects%2F56&utm_medium=PDF&utm_campaign=PDFCoverPages

Turkson‐Ocran, R. A. N., Spaulding, E. M., Renda, S., Pandian, V., Rittler, H., Davidson, P. M.,

... & D’Aoust, R. (2020). A 10‐year evaluation of projects in a doctor of nursing practice programme. Journal of clinical nursing, 29(21-22), 4090-4103. doi:10.1111/jocn.15435.