## Slide 1: Handbook of Informatics for Nurses & Healthcare Professionals
Seventh Edition
Chapter 8
Strategic Planning and Project Management Concepts for H I T and Quality Improvement Initiatives
Copyright © 2024 Pearson Education, Inc. All Rights Reserved
Notes: If this PowerPoint presentation contains mathematical equations, you may need to check that your computer has the following installed:
1) MathType Plugin
2) Math Player (free versions available)
3) NVDA Reader (free versions available)

## Slide 2: Learning Objectives (1 of 3)
8.1 Define strategic planning
8.2 Discuss the importance of strategic planning for health information technology (H I T)
8.3 Describe how strategic planning is related to an organization’s mission, scope, vision, goals, and objectives

## Slide 3: Learning Objectives (2 of 3)
8.4 Understand the relationship between strategic planning for information systems and planning the overall organization
8.5 Discuss four issues in strategic decision making
8.6 List three skills needed by an I N S that are important for project management

## Slide 4: Learning Objectives (3 of 3)
8.7 List two project management processes used in the quality improvement process
8.8 Discuss the role of quality improvement in healthcare
8.9 Discuss one consideration for the future of project management

## Slide 5: Overview of Strategic Planning
Chapter 8 describes the value of strategic planning when a H I T system is being considered
Concepts used in managing projects include
  Systems development life cycle (S D L C)
  Project management life cycle (P M L C)

## Slide 6: Issues in Strategic Decision Making
Interoperability
  Ability to exchange information across systems
Configurability
  The way software can be configured to adapt to meet the user’s needs
Usability—Ease of use
Information Blocking
  A practice or activity that prevents or interferes with the access, exchange, or use of electronic health information

## Slide 7: Planning at the Project Level—The Project Management Process (1 of 7)
Project and strategic planning
  Critical first steps in any planning process
Project Management Institute (P M I)
  Organizing and certifying organization that defines standards and methodologies
Stakeholders: Those who have a vested interest in the new project

## Slide 8: Planning at the Project Level—The Project Management Process (2 of 7)
S W O T analysis
  S W O T stands for strengths, weaknesses, opportunities, and threats
  Helps identify gaps in current system and potential opportunities in a new or updated system
Strategic thinking
  Requires continual assessment and application of new business acumens
  Must occur before strategic planning

## Slide 9: Planning at the Project Level—The Project Management Process (3 of 7)
Strategic plan components
  Developing project plan
  Risk management
  Communication plans
  Change-management process
  Implementation

## Slide 10: Planning at the Project Level—The Project Management Process (4 of 7)
Strategic plan components (continued)
  Monitoring and control strategies
  List of final deliverables
  Final close processes with evaluations
  Knowledge transfers

## Slide 11: Planning at the Project Level—The Project Management Process (5 of 7)
Strategic planning process for information management
  Most critical issue facing decision making for information systems
  Includes categorizing by must-haves and nice-to haves
    Must-haves are needed now
    Nice-to-haves can wait until the optimization phase

## Slide 12: Planning at the Project Level—The Project Management Process (6 of 7)
Goals and rationales for the system
  To support business and clinical decisions
  To make effective use of emerging technologies
  To enhance the organization’s image
  To promote satisfaction of market and regulatory requirements

## Slide 13: Planning at the Project Level—The Project Management Process (7 of 7)
Goals and rationales for the system
  To be cost-effective
  To provide a safer environment for patients

## Slide 14: The Role of the Informatics Nurse Specialists in Project Management (1 of 2)
Final steps of project management
  Implementing the plan
  Monitoring outcomes
  Evaluation and lessons learned with knowledge transfer

## Slide 15: The Role of the Informatics Nurse Specialists in Project Management (2 of 2)
Informatics Nurse Specialist (I N S)
  Assumes the project management (P M) role
  Facilitation among I T, nursing staff, and other departments
  Advocating for improving patient safety and satisfaction
Chief Nursing Informatics Offices (C N I O)
  Key decision maker
  Bridge between nursing and I T through relationships with the C E O, C I O and C N O

## Slide 16: Project Management Concepts As a Foundation for Quality Improvement (1 of 7)
Five phases
  Design/plan
  Implementation
  Monitoring and control
  Evaluation
  Lessons learned with knowledge transfer

## Slide 17: Project Management Concepts As a Foundation for Quality Improvement (2 of 7)
Metrics
Measures of success
Scope document—see next slide

## Slide 18: Project Management Concepts As a Foundation for Quality Improvement (3 of 7)
Scope Document
  Goals and objectives
  Mission
  Vision statement
  Sponsors
  Scope creep
  Gap analysis
  Current state
  Future state

## Slide 19: Project Management Concepts As a Foundation for Quality Improvement (4 of 7)
Phase 1
  Team selection
  Consultants
  Resource availability

## Slide 20: Project Management Concepts As a Foundation for Quality Improvement (5 of 7)
Phase 2
  Work breakdown structure (W B S)
    Gantt chart
  Communication plan
  Risk assessment and management plan
  Plan for change and change management
    Kotter’s eight stages
    Change control board (C C B)

## Slide 21: Project Management Concepts As a Foundation for Quality Improvement (6 of 7)
The Role of Quality Improvement in Healthcare
  To provide high-quality care to patients and improve the health of our population
  Involves a systematic and coordinated approach to solving a problem

## Slide 22: Project Management Concepts As a Foundation for Quality Improvement (7 of 7)
Using project management process and informatics for quality improvement
  Must be safe effective and responsive to needs
Key Performance Indicators
  Define goals and objectives
  Identify tasks
  Define the process
  Define the methods

## Slide 23: Future Directions (1 of 3)
The process for developing strategic plans described in this chapter is much the same for federal agencies
With the Affordable Care Act (A C A) as a driving force, the D H H S developed a strategic plan to define how it will address many evolving issues
  A “living” web document, frequently updated

## Slide 24: Future Directions (2 of 3)
Federal Health I T Strategic Plan for fiscal years 2020–2025
  Promote Health and Wellness
  Enhance the Delivery and Experience of Care
  Build a Secure, Data-Driven Ecosystem to Accelerate Research and Innovation
  Connect Healthcare and Health Data through an Interoperable Health I T Infrastructure

## Slide 25: Future Directions (3 of 3)
Continuing challenges in healthcare include
  Increased healthcare spending
  Poor health outcomes
  Increased rates of mental illness and substance use disorders
  Inconsistent access to care, technology, and information

## Slide 26: Copyright
This work is protected by United States copyright laws and is provided solely for the use of instructors in teaching their courses and assessing student learning. Dissemination or sale of any part of this work (including on the World Wide Web) will destroy the integrity of the work and is not permitted. The work and materials from it should never be made available to students except by instructors using the accompanying text in their classes. All recipients of this work are expected to abide by these restrictions and to honor the intended pedagogical purposes and the needs of other instructors who rely on these materials.